## Readme
Introduction
This template is dedicated to standardize estimation of development and QC efforts on company level and decrease amount of estimation errors.
Temaple utilizes best practices for "bottom up" (decomposition and recomposition) estimation approach that is commonly used in our company and is based on guidelines provided by Steve McConnel in his book "Software Estimation—Demystifying the Black Art" (http://books.softserveinc.com/browse/book/676)
Short User Guide
Step1: Populate "Input Data"
Open "Input Data" worksheet and review/update existing ratios for unit testing, code review , bug fixing and Manual QC testing activities.
"Input Data" worksheet already contains predefined default values which are based on average company data, but if you expect that % of efforts on Unit Testing, Code Review, Bug Fixing or Manual QC Testing will be different on your project, you can update these values according to your case.
Additional Notes:
If some practices (like Unit Testing or Code Review) will not be used on your project, just set "0%" for appropriate activity type
Bug Fixing = 15% is dedicated to cover ongoing "defects fixing" only and doesn't include efforts on stabilization phase(s)
Unit Testing = 25% (according to our average company data) means that target for code coverage by unit test is 70%-80%
Ratio for "Manual QC" efforts is dedicated to cover cases when QC efforts are estimated basing on development efforts estimate. Usually it happens on earlier project stages when QC staff are not assigned on project yet. If you are going to estimate QC efforts manually, just set "0%" in "Manual QC" efforts field
Step2: Estimate Development Efforts (for Developers, Tech Leads, Architects only)
Estimate "optimistic", "pessimistic" and "most likely" efforts in "man/days" (1 man/day = 8 working hours). Such gradation helps to avoid mistakes during project schedule and costs estimations.
Do not calculate "most likely" estimate (sometimes people take average value "(optimistic + pessimistic)/2") - usually it causes estimation errors. Rather, estimate its value.
Estimate efforts on implementation only! Efforts on "code review", "unit testing" and "bug fixing" will be auto-calculated and applied as adjustment to "Expected Efforts" estimate
Override auto-calculated "code review", "unit testing" and "bug fixing" estimate with your own estimate if you see that auto-calculated values are noticeably under or over estimated
Define dependencies between tasks/components/features in "Dependencies" column (just set # of appropriate task(s)/component(s)/feature (s) there). - it helps PM to estimate schedule and resources allocation properly. Use "coma-separated" numbers if your task/component/features depends on several other items
Use "insert row(s)" command (select row(s)->right mouse click ->Insert) if you need more rows in "Dev Efforts" table
Your scope of work must be decomposed on more than 10 items, otherwise the final estimate will not be accurate enough.
Step3: Estimate QC Efforts (for QC only)
Note: This step is optional if you are going to use estimate based on % from development efforts
Copy-paste items from dev efforts table which need to be tested. It will guarantee that you reserved efforts for testing of all components/features implemented by developers
Add your own additional QC specific tasks/activities
Estimate "optimistic", "pessimistic" and "most likely" efforts in "man/days" (1 man/day = 8 working hours). Such gradation helps to avoid mistakes during project schedule and costs estimations.
Do not calculate "most likely" estimate (sometimes people take average value "(optimistic + pessimistic)/2") - usually it causes estimation errors. Rather, estimate its value.
Define dependencies between tasks/components/features in "Dependencies" column (just set # of appropriate task(s)/component(s)/feature (s) there) - it helps PM to estimate schedule and resources allocation properly. Use "coma-separated" numbers if your task/component/features depends on several other items
Use "insert row(s)" command (select row(s)->right mouse click ->Insert) if you need more rows in "QC Efforts - Manual" table
Your scope of work must be decomposed on more than 10 items, otherwise the final estimate will not be accurate enough.
FAQ
Q1: I don't like this template. Can I use my own one?
Answer: Yes , you can use your own , if your template meets at least the following criteria:
Includes "Optimistic", "pessimistic" and "most likely" estimates
Calculates "Expected Estimate" basing on "Optimistic", "Pessimistic" and "Most Likely" estimates
Resulting estimates include efforts on "Unit Testing", "Code Review" and "Bug Fixing" if there was no decision from upper-management to go ahead without all/some of these practices
Q2: I want to group tasks/components/features by some logical criteria instead of using plain list. Can I do it?
Answer: Yes, sure. You can group your tasks/components/features as you wish. Just be sure that "Total" row, finally contains right "sum" values. We suggest to use the following simple guide to guarantee this:
- Estimate fields ("Optimistic", "Pessimistic", "Most Likely",...) for row that identifies "Group Name " should be "0" or "empty"
- If you need to show "total estimates" for your groups , update formulas in "Total" row to omit these "groups total estimates"
Q3: I need to add additional column in estimates table. Can I do it?
Answer: Yes, you can add any columns at any place before "Optimistic (man/days)" column or after "Final Expected (man/days)"
Q4: What does auto-calculated "Expected Estimate" mean?
Answer: That is 50%/50% estimate. It means that probabity that you underrun this estimate is 50% as well as probability that you overrun this estimate.
Q5: Why do we need to calculate standard deviation?
Answer: It provides more confidence in final estimate. Theoretically, if 99,7% of your actual outcomes fall within your estimation range (optimistic-pessimistic) and your "Expected Estimate" is truly 50% likely, it provides 98% of confidence in your "Final Recommended Estimate"
Q6: I'm going to estimating really big project and instead of estimation each specific UI form or business rule, I'm planning to separate them by complexity levels (like Very High, High, Medium, Low, Very Low) and estimate approximate efforts for each complexity level. How can I use this template in such case?
Answer: We suggest the following solution there:
Add additional worksheet(s) to this template like "UI Forms Estimation" or/and "Business Rules Estimation"
Then estimate "Optimistic ", "Pessimistic" and "Most Likely" efforts for each UI Forms/Business Rules complexity level there
Then calculate aggregative "Optimistic ", "Pessimistic" and "Most Likely" estimates for each complexity level there (multiply number of UI Forms/Business Rules of appropiate complexity on appropriate estimate):
"Aggregative Pessmistic Estimate for Very High Complexity UI Forms" = CountOfVeryHighComplexityUI Forms x OptimissticEstimateForVeryHighComplexityUIForm
Then add those aggregative estimates for each complexity level to "Dev Effors" worksheet
Q6: I have additional questions. Whom can I ask them?
Answer: Please contact Andriy Karyy (akaryy@softserveinc.com)

## Input Data
Activity Type | % from efforts on implementation
Unit Testing | 15%
Code Review | 20%
Bug Fixing | 15%
Activity Type | % from dev efforts
Manual QC | 30%
Comments
Default values here are based on average company data. If you expect that % of efforts on Unit Testing, Code Review, Bug Fixing and Manual QC Testing will be different, please update values according to your case.
If some practices (like Unit Testing or Code Review) will not be used on your project, just setup "0%" for appropriate activity type
Unit Testing = 25% means that target for code coverage by unit test is 70%-80%
Bug Fixing = 15% is dedicated to cover ongoing "defects fixing" only and doesn't include efforts on stabilization phase(s)

## Toolkit & Forseti Efforts
# | Decomposition Item | Expected deliverable | Comments | Dependencies | Optimistic (man/days) | Pessimistic (man/days) | Most Likely (man/days) | Expected (man/days) | Standard Deviation (Individual) | Variance (Standard Deviation Squared) | Unit Testing (man/days) | Code Review (man/days) | Defect Fixing (man/days) | Final Expected (man/days)
1 | Get familiar with the Healthcare Data Protection Suite
| Read Google Cloud Data Protection Toolkit guide | https://cloud.google.com/architecture/data-protection-toolkit-guide |  |  | 0.25 | 0.5 | 0.3 | 0.3 |  |  | 0 | 0 | 0.045 | 0.345
| Prepare local environment (download tools, get all necessary credentials, templates) | Documented approach in Confluence (will be) |  |  | 0.5 | 1 | 0.5 | 0.5 |  |  | 0.075 | 0.1 | 0.075 | 0.75
| Create the HCL template based on the examples (watch example movie) and HLD diagram | Documented approach in Confluence (will be), IaC code |  |  | 0.5 | 2 | 1 | 1 |  |  | 0.15 | 0.2 | 0.15 | 1.5
| Generate first code using TF Engine and read all generated README.md files | Documented approach in Confluence (will be) |  |  | 0.25 | 0.5 | 0.5 | 0.5 |  |  | 0.075 | 0.1 | 0.075 | 0.75
| Read document related to Toolkit limitations | Documented approach in Confluence (will be) |  |  | 0.25 | 0.5 | 0.25 | 0.25 |  |  | 0 | 0 | 0 | 0.25
Expected completion date
2 | Deploy DevOps project
| Setup all necessary parameters related to DevOps project, run TF Engine and login to the Cloud | Documented approach in Confluence |  |  | 0.5 | 1 | 0.625 | 0.625 | 0.33 | 0.11 | 0.09375 | 0.125 | 0.09375 | 0.9375
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.33 | 0.11 | 0 | 0 | 0 | 0.25
| Run Apply changes from terraform/devops directory | Documented approach in Confluence |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
| Change enable_gcs_backend to true and rerun tfengine and terraform apply again | Documented approach in Confluence |  |  | 0.5 | 1 | 0.6 | 0.6 | 0.33 | 0.11 | 0.09 | 0.12 | 0.09 | 0.9
Expected completion date
3 | Deploy groups configuration to the DevOps project
| Setup TF Engine template by adding people to the groups which will be used in the CI/CD project, run TF Engine | IaC code for groups |  |  | 0.125 | 0.5 | 0.25 | 0.25 | 0.33 | 0.11 | 0.0375 | 0.05 | 0.0375 | 0.375
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Run Apply changes from terraform/groups directory |  |  |  | 0.25 | 0.5 | 0.25 | 0.25 | 0.33 | 0.11 | 0.0375 | 0.05 | 0.0375 | 0.375
| Push all changes from terraform/ directory to the repository |  |  |  | 0.25 | 0.5 | 0.25 | 0.25 | 0.33 | 0.11 | 0.0375 | 0.05 | 0.0375 | 0.375
Expected completion date
4 | Deploy network project - for shared network config
| Setup TF Engine template and run TF Engine |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Apply changes by creating git PR |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
Expected completion date
5 | Deploy CI/CD configuration to the DevOps project
| Setup all necessary variables in the TF Engine template and generate terraform code |  |  |  | 0.5 | 1 | 0.625 | 0.625 | 0.33 | 0.11 | 0.09375 | 0.025 | 0.09375 | 0.8375
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Integrate code with the Git repository in CloudBuild |  |  |  | 2 | 3 | 2.5 | 2.5 | 0.33 | 0.11 | 0.375 | 0.1 | 0.375 | 3.35
Expected completion date
6 | Deploy audit project
| Setup TF Engine template for audit project (remember about naming limitations) and run TF Engine | IaC code for Audit project |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Apply changes by creating git PR |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
Expected completion date
7 | Deploy monitoring project (forseti included)
| Setup TF Engine template and run TF Engine |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Apply changes by creating git PR |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
| Solve all problems related to Forseti configuration |  |  |  | 1 | 2 | 1 | 1 | 0.33 | 0.11 | 0.15 | 0.2 | 0.15 | 1.5
Expected completion date
8 | Deploy projects for prod/dev/other environments
| Setup TF Engine template and run TF Engine |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
| Rewrites all Terraform configuration files to a canonical format | Documented approach in Confluence |  |  | 0.125 | 0.25 | 0.125 | 0.125 | 0.33 | 0.11 | 0.01875 | 0.025 | 0.01875 | 0.1875
| Apply changes by creating git PR |  |  |  | 0.5 | 1 | 0.5 | 0.5 | 0.33 | 0.11 | 0.075 | 0.1 | 0.075 | 0.75
[8 empty] | 0 | 0.33 | 0.11 | 0 | 0 | 0 | 0
| Expected completion date | [6 empty] | 0 | 0.33 | 0.11 | 0 | 0 | 0 | 0
9 | Prepare the policy-library and rules for Forseti
| Get familiar with Forseti policy-library and rules |  |  |  | 1 | 2 | 1.5 | 1.5 |  |  | 0.225 | 0.3 | 0.225 | 2.25
| Create list and definition of necessary policies-library and rules |  |  |  | 3 | 5 | 4 | 4 |  |  | 0.6 | 0.8 | 0.6 | 6
| Copy prepared list to the bucket |  |  |  | 1 | 2 | 1.5 | 1.5 |  |  | 0.225 | 0.3 | 0.225 | 2.25
10 | Prepare production code
| Solve all problems facedwhen working on the previous steps |  |  |  | 2 | 4 | 3 | 3 |  |  | 0.45 | 0.6 | 0.45 | 4.5
| Create code base not related to the external components like forseti modules etc |  |  |  | 4 | 8 | 6 | 6 |  |  | 0.9 | 1.2 | 0.9 | 9
| Create runbook for the new code base |  |  |  | 2 | 3 | 2.5 | 2.5 |  |  | 0.375 | 0.5 | 0.375 | 3.75
11 | Testing
| Detsrmine and list test scenarios |  |  |  | 4 | 8 | 6 | 6 | 0.33 | 0.11 | 1 | 0.4 | 0.6 | 8
| Run and document application tests |  |  |  | 4 | 8 | 6 | 6 | 0.33 | 0.11 | 1 | 0.4 | 0.6 | 8
Expected completion date
| Total |  |  |  | 33 | 64 | 44.275 | 44.275 | [5 empty] | 63.5575
Standard Complex Deviation | [13 empty] | 1,94
Final Recommended Estimate (man/days) | [13 empty] | 44.275
Final Optimistic Estimate (man/days) | [13 empty] | 33
Final Pessimistic Estimate (man/days) | [13 empty] | 64